# Mock Meeting Script: Harvest Ridge Improvement Plan Check-in

Company: FreshCart (fictional grocery delivery business)

Roles: 3 volunteers - Arjun Shah (Chair), Meera Iyer, Deepak Verma

Length: About 5 minutes, read at a natural pace

Instructions for volunteers: read your lines naturally, as if in a real call. Small pauses and a little back-and-forth are fine. Record this with Teams transcription or recording turned on, so Copilot has a transcript to work from.

# Roles

Arjun Shah - FreshCart Operations Manager, chairing the meeting

Meera Iyer - FreshCart Procurement Lead

Deepak Verma - Owner, Harvest Ridge Produce (the fruit supplier)

# Script

Arjun: Thanks both for joining. This is our check-in on the Harvest Ridge improvement plan following the Q3 supplier review. Deepak, can you give us an update on where things stand?

Deepak: Sure. On-time delivery has improved a bit since the review, we're being more careful with the Monday and Friday routes especially. The main fix is still the second vehicle.

Meera: Right, and our understanding from the Q3 report was that the second vehicle would be in service from the first of November. Is that still on track?

Deepak: Actually, we've had a delay with the vehicle registration. It's now looking like the first week of December rather than November. I know that's later than what we discussed.

Arjun: That's a concern, December is right in the middle of the festive peak. Can you say more about why it slipped?

Deepak: It's mostly paperwork with the transport authority, not a cost issue. We're pushing to get it sorted faster if we can.

Meera: Okay. In the meantime, are Monday and Friday still the worst days for us?

Deepak: Yes, those are the two days our single vehicle is under the most pressure, so any delay or breakdown affects the whole morning's deliveries.

Arjun: Understood. Let's keep the weekly on-time tracking going regardless. Meera, can your team keep sending Deepak the numbers each Friday?

Meera: Yes, I'll keep that going.

Deepak: That's helpful, it lets us see where we're slipping in real time.

Arjun: One more thing - given the delay, I think we should get the revised improvement plan looked at properly before we finalise anything. Someone should probably get it reviewed on our side.

Meera: Agreed, that makes sense given the changed timeline.

Arjun: Good. Let's touch base again in two weeks to see where the vehicle registration stands.

Deepak: Sounds good. I'll aim to have clearer news on the registration by then.

Meera: Great, so we're set for early November for the next check-in then.

Arjun: Thanks both, that's everything from my side. Talk soon.

End of script. All names, figures and events are fictional and created for training purposes.